## Slide 1: Status of E-XFEL Module Assembly at Saclay
O. Napoly, CEA-Saclay, IRFU/SACM

## Slide 2
2
European XFEL Layout

## Slide 3
Superconducting Linear Accelerator
1+80 cryomodules
8+640 cavities
1.3 GHz / 24.3 MV/m
20 RF stations (10 MW) operating at 5,2 MW
1 cryogenic sector : 120 W @2K, 204 W @5-8K, 1,4 kW @40-80K
1
1
5
648 RF couplers
120 kW @ 5 mA
18-38 m underground

## Slide 4: CEA contributes to the XFEL Cold Linac construction through Cavity String Assembly (WP9) and Module Assembly (WP3)  Accelerator Module Assembly of 3+80 accelerator modules with 1 per week throughput ! operated by an industrial contractor on the Saclay site.

## Slide 5: Project Timeline
Our effort develops over the 3 phases:
Phase 1: Preparation of Infrastructure and Tooling
 April 2010
Phase 2: Training and Commissioning of XFEL Village at Saclay with XFEL Prototype Modules (PXFEL2 and PXFEL3)
August 2010  end 2011
leading to Restricted Call for Tender for Assembly Contract
by Q2-2011
Phase 3: XFEL module assembly by indial. contractor
Q1-2012  Q3-2014

## Slide 6: Industrialization Baseline
Build the Assembly Tool adapted to the goal of 1 module/week
  normal mode  7 workstations for 7 week assembly time
  degraded mode  doubling of most workstations
Review assembly procedures to avoid variations and other sources of man errors
 long training phase with prototype modules
 pre-industrialization phase with pre-series modules
 optimize procurement of pre-fabricated parts
Implement personnel safety regulations ahead of contract.

## Slide 7: Optimisation Rationale
Comply with XFEL project schedule and DESY procedures
 limited room for unproven innovation
Tailored to Saclay pre-existing hall layout
 three buildings around a central courtyard
Optimized for cost (manpower) effectiveness
 7 (maybe 6) week total assembly time
Optimized for assembly fluidity
 alternating workstation occupation
Adaptive facility towards future projects
 maximum module length = 15 m

## Slide 8: Phase 1: Preparation of Infrastructure and Tooling

## Slide 9: Overview of the Assembly Buildings
XFel Village
3
2
4
6
5
Bldg 124 North
25x15 m²
Bldg 126 North
40x11 m²
7
Bldg 126 South 30x17 m²
8
1
CourtYard
6b
©GoogleMap
Clean rooms
Assembly halls
Offices
Warehouse

## Slide 10: Assembly Hall : Workstations
AL-WS1+2
CO-WS1
CO-WS2
RO-WS1+2
CA-WS1
SH-WS1+2
Ware
house

## Slide 11: Organisation of Work Stations
Clean Room Cold Coupler Area (IS04-CC-WS1)
  Cold coupler assembly
Clean Room String Assembly Area (ISO4-SA-WS1, ISO4-SA-WS2)
Roll-out Area (RO-WS1, RO-WS2)
  HOM adjustment, magnetic shielding, tuners,…
  2Ph-tube welding, cold-mass/string connection
Alignment Area (AL-WS1, AL-WS2)
  Cavity and quadrupole fine alignment
  Coupler shields and braids, tuner electric tests
Cantilever Area (CA-WS1)
  Welding of 4K and 70 K shields, super insulation
  Insertion into vacuum vessel and string alignment
Coupler Area (CO-WS1, CO-WS2)
  Warm couplers + coupler pumping line
  Quad current leads
Shipment Area (SH-WS1, SH-WS2)
  Instrumentation
  Control operations (electrical, RF), “acceptance test”
  End-caps closing, N-insulation, loading.

## Slide 12: Clean Room : Work Stations
ISO4-CC-WS1
Coupler cold part assembly
(8 cavities / week)
ISO4-SA-WS1
Cavity string assembly
(1 string / week)
Cavity washer
Unpacking / packing and cleaning pieces
Cavity storage
ISO4-SA-WS2
2nd week string assembly

## Slide 13: Clean Room Layout
ISO 7
(class 10 000)
28 m2
5.92 m x 4.72 m
ISO 5
(class 100)
38 m2
7.72 m x 4.72 m
ISO4 (Class 10)
112 m²
7.8 m x (6.6+7.8) m
15.6 m

## Slide 14: Clean Room constructed (Sept’09)

## Slide 15: Big Tools Fabrication
«INFN-DESY» Cantilever system and «FNAL» transfer frame
with M8* (no string), May 2010 with PXFEL2, October 2010
(left) (right)

## Slide 16: Big Tools Fabrication
«CEA» transfer carriage «INFN-DESY» red girder
with PXFEL2 cold mass and cavity string (october 2010)
First girder (out of 3 units) + 4 sets of pillars + transfer frame
delivered to Saclay in June 2010.
Electric transfer carriage delivered to Saclay in Nov. 2010.

## Slide 17: Phase 2: “XFEL Village” Commissioning with Prototype Modules (PXFEL 2, PXFEL3)

## Slide 18: 2008-2009 : Assembly Training at DESY
About two years of observation and participation to the assembly operations on M3***, M8**, PXFEL1-3 at DESY by Saclay staff, including HH-Saclay-HH transports.
From Hans Weise’s LINAC’10 presentation:
Actually not correct:
First training to string assembly (clean room) authorized for PXFEL3.
Observation only on PXFEL2 string assembly.

## Slide 19: Assembly prototyping at Saclay
Assembly of XFEL prototype cryomodules (PXFEL2 and
PXFEL3) at Saclay aims at:
  Completing the training of the Saclay team;
  Commissioning the infrastructure (XFEL Village)
The team (~10 persons) has started the disassembly of PXFEL2 on August 24th, with continuous help of DESY staff.
Current status on PXFEL2 disassembly and re-assembly:
  Cavity string rolled-in and out of the clean room
  Tuners assembly on October 28th
  String to cold mass (week 45)
  Cavity alignment (week 50)
PXFEL3 assembly from “kit” foreseen for beginning of 2011

## Slide 20: Assembly prototyping at Saclay
Venting of cavity string
Coupler dis-assembly

## Slide 21: Assembly prototyping at Saclay
Vacuum vessel roll-outs and roll-ins
Cutting of Al thermal shields

## Slide 22: Assembly prototyping at Saclay
Transfer of cold mass + cavity string to clean room hall.
(electrical transfer vehicle due next week)

## Slide 23: Assembly prototyping at Saclay
Transfer of cold mass + cavity string on Roll-out Area
(cavity posts from DESY)

## Slide 24: Assembly prototyping at Saclay
Roll-in of cavity string in IS04 Area

## Slide 25: Assembly prototyping at Saclay
Tuner assembly

## Slide 26: Assembly Prototyping at Saclay
Superinsulation blankets try-on

## Slide 27: Phase 3: XFEL Module Assembly by an Industrial Contractor

## Slide 28
Ramping up industrial assembly
P1: assembly of 3 pre-series modules in sequence for training of the first ½ teams by CEA and DESY personnel, assuming 7 week assembly interleaved by 3 weeks for CMTB qualification.
P2: assembly of 5 modules in parallel during a ramp-up period (P2) for training of the second ½ teams by the first ½ teams, assuming 2 week assembly per module.
P3: assembly 75 modules in parallel at the rate of 1 module/week.
Period 1: assembly of 3 pre-series modules, in sequence, interleaved with CMTB tests
Period 2: parallel assembly of 5 modules Period 3: // assembly of 75 modules 1/week

## Slide 29: Summary
Christmas early this year, plenty of new toys !

## Slide 30: Acknowledgments
Considerable help received from DESY, thanks to
C. Engling, K. Jensch, W. Maschmann & Cie
A. Matheisen, M. Schmöckel & Cie
and M. Schlösser, H. Weise, …
and from FNAL, thanks to T. Arkan
Thanks to my CEA colleagues: S. Berry, J.P. Charrier,
P. Contrepois, S. Cozette, M. Fontaine, C. Madec,
Y. Sauce, T. Vacher, B. Visentin, and A. Daël, …

## Slide 31: Acknowledgments